## Sheet1
Nr (D/E ) | Dissemination and exploitation of results (D/E ) | NR (E/R) | Expected results (E/R) | Target group(s) / potential beneficiaries | projekta laiks | koriģētais laiks | Milestone
|  |  | Milestone 1 The project start |  | 2011-10-01
1 | Report in project Website | 1 | Updated Project Activity Plan | Project partners | 2011-10-07 | compleete | 2 | Ok
2 | Report in project Website | 2 | Contract between Leonardo da Vinci agency and the project promoter | The project promoter, Leonardo da Vinci Agency | 2011-10-07 | compleete | 2 | OK
3 | Report in project Website | 3 | Bilateral contracts among the partners and the project promoter | The project partners | 2011-10-28 | compleete | 2 | OK
10 | Report in project Website | 10 | The minutes of the 1st workshop | The project partners | 2011-11-01 | compleete | 2 | OK
27 | Izveido plāna variantus dažādām ieinteresētajām grupām. Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet un biznesa ceļojumu laikā | 27 | Dissemination and Exploitation plan | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2011-11-01 | compleete | 2 | OK
|  |  | Milestone 2 Start-up procedures are completed | -Contract between Leonardo da Vinci agency and the project promoter; -Updating of the Project Activity Plan; -Bilateral contracts among the partners and the project promoter; -The 1st workshop;-Development of the project web-page structure; -Finalizing of the valorisation plan; | 2011-11-12
9 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet | 9 | The questionnaire for SMEs | The project partners; Entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. | 2011-11-26 | compleete | 3 | OK
23 | Ziņojumi masu mēdijos vai uzstāšanās pasākumos kur informē par Website | 23 | The project Website | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2011-12-10 | compleete | 3 | OK
24 | Projekta partneru atskaite par leafletu izplatīšanu | 24 | Project leaflets | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2012-02-11 | 2013-02-15 | 3
6 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet | 6 | Curricula of the courses | The primary target groups are entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups are vocational training institutions, distance education centres, business support centres | 2012-02-18 | compleete | 3 | Ok
7 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet | 7 | The methodological requirements for the training modules | The project partners; Entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups are vocational training institutions, distance education centres, business support centres | 2012-02-18 | compleete | 3 | OK
8 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet | 8 | The technological requirements for the training modules | The project partners; Entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups are vocational training institutions, distance education centres, business support centres | 2012-02-18 | compleete | 3 | OK
5 | Ziņojumi masu mēdijos vai uzstāšanās konferencēs vai workshop (uzraksta rakstu un partneri noziņo pie iespējas savās konferencēs) | 5 | The report on fact−finding and need−specification to define SMEs needs | The project partners; Entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups are vocational training institutions, distance education centres, business support centres | 2012-02-22 | compleete | 3 | OK
11 | Report in project Website | 11 | The minutes of the 2nd workshop | The project partners | 2012-02-29 | compleete | 3 | OK
|  |  | Milestone 3 Fact−finding and need−specification are completed | -Finalizing of the questionnaire for SMEs;-Conducting in-depth interviews with stakeholders ; -Development of the methodological requirements to the training modules;-Development of the technological requirements to the training modules;-Analysis of results of in-depth interviews; -Preparation of the report on fact−finding and need−specification; -The 2nd workshop;-Approval of the report on fact-finding and need specification by partners;-Design of the project logo;-Development of the project web-page content; -Translation of the project web-page content to national languages; -The project web-page publication;-Development and publication of the project leaflet; | 2012-03-01
19 | Report in project Website; partneru iepazīstināšanas pasākumi; apmācības veikšana | 19 | Guidelines for organization of training module testing in pilot groups | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2012-08-23 | 2013-03-15 | 4
22 | Report in project Website | 22 | The minutes of the 3rd workshop | The project partners | 2012-08-30 | compleete | 4 | OK
|  |  | Milestone 4 The draft versions of the all modules are completed | -Review content of the modules taking into account results of needs analysis;-Updating of the existing training modules;-Translation of all modules to English;-Interim audit by Leonardo da Vinci agency;-The 3rd workshop;-Information in the mass media on the results of the need-specification and project status;-Project interim report; | 2012-10-19
20 | Ziņojumi masu mēdijos vai uzstāšanās konferencēs (uzraksta rakstu un partneri noziņo pie iespējas savās konferencēs) | 20 | Report of training module testing in pilot groups | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2012-12-21 | 2013-04-15 | 5
|  |  | Milestone 5 The final versions of all modules are developed | -Testing of training modules in national pilot groups;-Development of the testing report;-Information in the mass media on the training modules and project status;-Preparation and publication information on the project conference; | 2012-12-22
12 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet un biznesa ceļojumu laikā | 12 | Information Literacy for SMEs (Updated training module) | The primary target group: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-04-13 | 2013-04-15 | 6
13 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet un biznesa ceļojumu laikā | 13 | Information Technologies in Management and Business Administration of SMEs (Updated training module) | The primary target group: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-04-13 | 2013-04-15 | 6
14 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet un biznesa ceļojumu laikā | 14 | Computer Based Project Management (Updated training module) | The primary target group: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-04-13 | 2013-04-15 | 6
15 | Report in project Website; partneru iepazīstināšanas pasākumi; apmācības veikšana | 15 | Distance education web environment | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-04-15 | 2013-04-15 | 6
18 | Report in project Website; partneru iepazīstināšanas pasākumi; apmācības veikšana | 18 | Computer Based Project Management (Training module implemented into the web environment) | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-05-18 |  | 6
16 | Report in project Website; partneru iepazīstināšanas pasākumi; apmācības veikšana | 16 | Information Literacy for SMEs (Training module implemented into the web environment) | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-05-18 |  | 6
17 | Report in project Website; partneru iepazīstināšanas pasākumi; apmācības veikšana | 17 | Information Technologies in Management and Business Administration of SMEs (Training module implemented into the web environment) | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-05-18 |  | 6
25 | Atskate par konferenci | 25 | Materials of the project conference | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-05-22 |  | 6
28 | Izsūtīšana ieinteresētajām organizācijām; ziņojumi Internet un biznesa ceļojumu laikā | 28 | Promotion plan of the project results after the end of the project and commercialization | The project partners; the primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-07-21 |  | 6
26 | Report in project Website | 26 | The minutes of the 4th workshop + project conference | The project partners | 2013-07-28 |  | 6
21 | Report in project Website | 21 | Reports of the monitoring visits | The project partners | 2013-08-13 |  | 6
4 | Report in project Website | 4 | Project interim and final reports | Leonardo da Vinci agency; The project partners | 2013-09-29 |  | 6
29 | Formāli šeit ietilpst visi jau minētie pasākumi masu mēdijos. At least 20 various information units during the project implementation | 29 | Information in the mass media on the project | The primary target groups: entrepreneurs and employees of SMEs, as well as teachers who will introduce new vocational courses. Secondary target groups: vocational training institutions, distance education centres, business support centres | 2013-09-29 | in process | 6
|  |  | Milestone 6 The end of the project activities | -Translation of all modules to the national languages;-Implementation of the training modules into the web-environment;-Dissemination of the project results among the target groups; -The final conference;-Finalizing of the training modules and publication on the web;-The 4th workshop;-Project final report; | 2013-09-30
|  |  | Milestone 7 The end (out of project time) | -Final audit by Leonardo da Vinci agency;-The final transfer of project finance to the partners. | 2013-11-11